## PB 2010
Product BackLog
Autor: team Innovators
Date: 2012
Last update: 15.04.2012
#ID | Features | Description | By | Rank | Category | Estimate | Status | Note
#01 | Dynamic work with AST tree with Lua |  | LT | 432 | A | 5 | working
#02 | Parallelism for full text analysis |  | LT | 420 | A | 3 | done
#03 | Parallelism for blocks update |  | LT | 410 | A | 5 | working
#04 | New type of grammar - ToDo list |  | LT | 389 | A | 4 | working
#05 | Shortcuts and actions defined with Lua |  | LT | 365 | A | 3 | working
#06 | Refactoring |  | LT | 320 | B | 1 | done
#07 | Create new UI design |  | LT | 480 | A | 1 | done
#08 | Bug report |  | LT | 300 | B | 1 | done
#09 | New help on-line |  | LT | 449 | A | 1 | done
#10 | About window |  | LT | 260 | B | 1 | done
#11 | About this version |  | LT | 256 | B | 1 | done
#12 | New toolbars | for Editor, format, basic, tools | LT | 265 | B | 1 | done
#13 | CMD |  | LT | 266 | B | 1 | done
#14 | Fullscreen |  | LT | 267 | B | 1 | done
#15 | Start page |  | LT | 300 | B | 1 | done
#16 | New modern icons |  | LT | 340 | B | 1 | done
#17 | Zoom in / out |  | LT | 261 | B | 1 | done
#18 | Show Licence |  | LT | 150 | C | 2 | done
#19 | Bug list |  | LT | 110 | C | 3 | working
#20 | Task list |  | LT | 120 | C | 3 | working
#21 | Multitab editor |  | LT | 453 | A | 2 | done
#22 | Undo/redo/ copy/ paste ... |  | JK | 489 | A | 2 | done
#23 | Find |  | JK | 451 | A | 1 | done
#24 | Find & replace |  | JK | 452 | A | 2 | working
#25 | Syntax hightlighting | for keyword | JK | 436 | A | 2 | working
#26 | Options | for setting TrollEdit (font, size icons ...) | JK | 222 | B | 2 | working
#27 | Update for program |  | JK | 159 | C | 1 | working
#28 | Tree for file browser |  | JK | 165 | C | 1 | working
#29 | Text mode |  | JK | 478 | A | 1 | open
#30 | Context menu |  | JK | 452 | A | 1 | open
#31 | New Window | open new instance a program | JK | 234 | B | 1 | working |  | Actual working
#32
#33 | Tips & Tricks |  | JK | 50 | C | 1
#34 | i18n | for Slovak, CZ | JK | 60 | C | 4
#35 | Splitter | divided workspace | JK | 12 | C | 1
#36 | Simple Intellisense |  | JK | 44 | C | 5
#37 | Support language snippets |  | JK | 56 | C | 5
#38 | Import & Export of setting |  | JK | 77 | C | 4
#39 | Bookmarks | for toggle between bookmarsk in code | JK | 43 | C | 5
#40 | SW metric |  | JK | 22 | C | 5
#41 | Spell checker |  | JK | 11 | C | 5
#42 | Line numers for code |  | JK | 198 | C | 2
#43 | Create snapshot | save all files on workspace to config file | JK | 125 | C | 5
#44 | Show properties of file | metadata as size, autor, date ... | JK | 159 | C | 5
#45
#46
#47
#48
#49
#50
#51
#52
#53

## Legenda
Legenda
By - autor which insert feature |  | LT - Lukáš Turský, JK - Jozef Krajčovič
Rank - from 1 to 500 for each category
Category:
A - hight featrue | Rank for this category is - form 350 till 500
B - medium feature | Rank for this categorz is - form 200 till 350
C - low feature | Rank for this category is - form 1 till 200
Estimate - how time , unit is Days