## Hárok1
Functionality | Benefits | Prirority |  |  | Status
|  | must be | should be | nice to have
CORE implementation
Dynamic work with AST tree through Lua | Faster and mainly non-blocking work | x |  |  | WORKING
Parallelism for full text analysis | Faster content analyzing | x |  |  | DONE
Parallelism for blocks update | Faster update of analyzed blocks |  | x |  | WORKING
New type of grammar - ToDo list | Simple and easy to view ToDo list with user tasks, which are fast to create and parsed by given grammar | x |  |  | WORKING
Shortcuts and actions defined with Lua | Ability to add user defined shortcuts and actions |  | x |  | WORKING
Refactoring | Better code understanding | x |  |  | DONE
Text operations (undo, redo, copy, paste) | Incorporate conventions with text manipulation as used from normal text editors | x |  |  | DONE
Block operations (undo, redo) | Incorporate manipulation conventions into graphical mode of editor in the same way as for textual mode |  | x |  | INITIALIZED
User Interface - GUI
Create new UI design | Newer and better looking UI for better visual experience | x |  |  | DONE
Bug report |  |  |  | x | WORKING
New help on-line |  |  |  | x | WORKING
About window |  |  |  | x | DONE
About this version |  |  |  | x | DONE
Redesign menu bar and add new items |  | x |  |  | DONE
CMD |  |  |  | x | DONE
Fullscreen |  |  | x |  | DONE
Start page |  |  | x |  | DONE
New modern icons |  | x |  |  | DONE
Zoom in / out |  |  | x |  | DONE
Project tree |  |  |  | x | WORKING
Bug list |  |  |  | x | WORKING
Task list |  |  |  | x | WORKING
Multitab editor |  |  | x |  | DONE